## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Tariq Mansoor | 2026-09-04 | Dual-portal role switcher button state remained unchanged after clicking on smaller screen viewports. | Sprint 1 | Vishnu | User Interface | Added responsive media query classes and fixed mobile tap handler. | 2026-09-05 | Closed | Verified across mobile and desktop breakpoints.
2 | Vance Sterling | 2026-09-07 | De-allocating an operative when capacity was 30% resulted in a negative capacity value (-5%). | Sprint 1 | Vishnu | Logical | Wrapped subtraction logic in Math.max(0, current - 35). | 2026-09-07 | Closed | Unit test added for zero-boundary condition.
3 | Dr. Elena Rostova | 2026-09-18 | Overload warning badge did not render when capacity hit exactly 101%. | Sprint 2 | Vishnu | Logical | Updated threshold condition from > 105 to > 100. | 2026-09-18 | Closed | Critical burnout alarm triggers accurately.
4 | Tariq Mansoor | 2026-09-21 | RAG Ops room terminal crashed when prompt contained special regex characters. | Sprint 2 | Vishnu | Standards | Sanitized input string before running vector keyword matching. | 2026-09-22 | Closed | Handled special characters gracefully.
5 | Vance Sterling | 2026-09-24 | Operative stress index calculation was missing integer rounding, creating long floating-point numbers. | Sprint 2 | Vishnu | Maintainability | Applied Math.round() to stress index calculation formula. | 2026-09-24 | Closed | Values now display cleanly as integers (e.g., 28 PSI).
6 | Kaelen Chen | 2026-10-02 | Autonomous mail composer body did not update immediately when switching tones between Formal and Empathetic. | Sprint 3 | Vishnu | Logical | Added useEffect hook to re-generate template text on tone state change. | 2026-10-03 | Closed | Tone updates in real-time preview.
7 | Tariq Mansoor | 2026-10-05 | Mission Forge date picker allowed choosing past dates for target project completion. | Sprint 3 | Vishnu | User Interface | Added min date constraint attribute set to current timestamp. | 2026-10-06 | Closed | Prevents invalid past deadline selections.
8 | Dr. Elena Rostova | 2026-10-08 | Backend /api/matrix/toggle returned 500 error when non-existent operative ID was passed. | Sprint 3 | Vishnu | Logical | Added defensive check returning HTTP 404 with descriptive error JSON. | 2026-10-08 | Closed | Clean exception handling implemented.