## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency |  | Status
Sprint 1 | Sprint 1 | US-01 | As an HR Commander, I want a dual-role authentication and portal switcher so that Managers and Operatives access distinct interfaces. | Must have | None | Vishnu | Done
Sprint 1 | Sprint 1 | US-02 | As a System Admin, I want foundational agent orchestration (Planning, Research, Analysis, Decision) to structure multi-agent pipelines. | Must have | None | Vishnu | Done
Sprint 1 | Sprint 1 | US-03 | As an HR Commander, I want a Mission Forge to configure initiatives with deadlines, budgets, difficulty tiers, and required capacity slots. | Must have | US-01 | Vishnu | Done
Sprint 2 | Sprint 2 | US-04 | As a Resource Manager, I want a dynamic Resource Allocation Matrix with visual indicators when an employee exceeds 100% capacity. | Must have | US-03 | Vishnu | Done
Sprint 2 | Sprint 2 | US-05 | As an AI Lead, I want a shared memory repository (short-term session cache & long-term policy vectors) for contextual agent reasoning. | Must have | US-02 | Vishnu | Done
Sprint 2 | Sprint 2 | US-06 | As a Systems Engineer, I want enterprise tool integration (FinOps budget audit, HRMS lookup, SMTP dispatch) for autonomous actions. | Should have | US-02, US-05 | Vishnu | Done
Sprint 3 | Sprint 3 | US-07 | As an Operative (Employee), I want an RPG-style workspace with proficiency radar metrics, bandwidth sliders, and internal career quest logs. | Should have | US-01 | Vishnu | Done
Sprint 3 | Sprint 3 | US-08 | As an Executive, I want a natural language Multi-Agent RAG terminal displaying real-time agent thought traces (Thought -> Action -> Result). | Must have | US-05, US-06 | Vishnu | Done
Sprint 3 | Sprint 3 | US-09 | As an HR Director, I want an autonomous mail composition agent that drafts tailored onboarding and allocation notices upon team assignment. | Should have | US-04, US-06 | Vishnu | Done
Sprint 3 | Sprint 3 | US-10 | As a QA Engineer, I want REST API endpoints (/api/state, /api/matrix/toggle, /api/rag/query) for external enterprise workflow invocation. | Could have | US-08 | Vishnu | Done

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date |  | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | TS-101 | Setup Next.js/React repo & Cyber HUD Tailwind CSS theme | 2026-09-01 | 2026-09-02 | Vishnu | Development | Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | TS-102 | Implement role toggle header (Commander vs Operative) | 2026-09-07 | 2026-09-12 | Vishnu | UI Design | Completed | 6 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | TS-103 | Design Planning and Research Agent classes & prompt templates | 2026-09-17 | 2026-09-22 | Vishnu | AI Pipeline | Completed | 10 | 0 | 3 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | TS-104 | Develop Analysis and Decision Agent reasoning pipelines | 2026-09-27 | 2026-10-02 | Vishnu | AI Pipeline | Completed | 12 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | TS-105 | Create Mission Forge UI modal with tech stack & slot selector | 2026-10-04 | 2026-10-06 | Vishnu | Frontend | Completed | 8 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | TS-106 | Implement project state persistence in memory & LocalStorage | 2026-10-08 | 2026-10-10 | Vishnu | Backend | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
US-01 | TS-107 | Sprint 1 Integration testing & demo smoke test | 2026-10-12 | 2026-10-12 | Vishnu | QA & Review | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0
Formulas:
Task Start Date = [Task Completion Date, row above]+5
Task Completion Date = [Task Start Date]+5

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Tailwind CSS build issues with custom backdrop blur classes | Pinned Tailwind CSS configuration and imported custom .cyber-glass CSS utilities
Sprint 1 | Day 5 | Planning Agent hallucinated invalid task dependencies during goal decomposition | Added Pydantic schema validation and constrained prompt instructions
Sprint 2 | Day 3 | Allocation Matrix state race conditions when multiple slots were toggled rapidly | Wrapped allocation updates in atomic React state setters and backend locking
Sprint 2 | Day 7 | High API latency when querying mock vector store for candidate resumes | Implemented in-memory vector index cache with keyword fallback heuristics
Sprint 3 | Day 4 | Overload banner was not clearing when an operative was de-allocated | Corrected state synchronization logic in toggleAssignment handler

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-09-01 | 2026-09-12 | Vishnu | Documenting agent input/output contract schemas early | Hardcoding agent prompt templates directly in UI components | Daily 15-minute syncs on dependency blockers | Created centralized prompt repository in server/agentPrompts.js
2 | Sprint 2 | 2026-09-15 | 2026-09-26 | Vishnu | Automated unit testing for capacity calculation algorithms | Manually smoke-testing allocation state transitions | Cross-functional code reviews for AI prompt changes | Added automated unit test suite verifying capacity > 100% warnings
3 | Sprint 3 | 2026-09-29 | 2026-10-10 | Vishnu | End-to-end integration recording for evaluator presentation | Delaying styling polish until the final sprint day | Building modular UI components with Lucide icons | Packaged complete runnable zip with documentation and demo scripts